## JOB REQUEST
S/N | DATE | CS NUMBER | JOB DESCRIPTION | BRK NUMBER | STATUS (PENDING, PO ISSUED) | PO NUMBER | PO VALUE | VENDOR | JOB EXECUTION (PENDING, IN PROGRESS, DONE) | JCC COMPLETED (YES/NO) | PAYMENT COMPLETED (YES/NO) | REMARKS / VENDORS IN BRK
1 | 2026-01-06 | MCS11257 | Chemical cleaning of boiler 1, 2, 3. 4 & 5 at Utility | BRK05554 | PO ISSUED | PO252743 | 22333796.88 | CLEAKTEK | IN PROGRESS
2 | 2026-01-06 | MCS11258 | Calibration of boiler and air receiver pressure safety relief valves in Utility | BRK05555 | PO ISSUED | PO252483 | 2167200 | NAFIX | IN PROGRESS
3 | 2026-01-06 | MCS11259 | Annual inspection of boiler 1, 2, 3, 4 & 5 at Utility MPI & UT test | BRK05556 | PO ISSUED | PO252482 | 3780000 | NAFIX | IN PROGRESS
4 | 2026-01-06 | MCS11260 | Calibration of PMS tank and flowmeter in JNSD and Snacks | BRK05553 | PO ISSUED | PO252479 | 850000 | NAFIX | DONE | YES | YES
5 | 2026-01-08 | MCS11261 | Boiler 1, 2, 3, 5, Vam 2, 3 burner calibration and emission test at Utility | BRK05564 | PO ISSUED | PO252794 | 11287500 | MIZAMI | PENDING
6 | 2026-01-08 | MCS11262 | Maintenance of scrubber units at ETP | BRK05565 | PO ISSUED | PO252659 | 1420000 | TEKNOSPEK | DONE | YES | YES
7 | 2026-01-08 | MCS11263 | Annual inspection, NDT test of Vam 1, 2, 3, 4 HTG and condenser tubes at Utility | BRK05566 | JOB REQUEST ABANDONED
8 | 2026-01-08 | MCS11264 | Labour for heavy-duty preventive maintenance jobs in Utility | BRK05567 | PO ISSUED | PO252741 | 6060000 | TEKNOSPEK | IN PROGRESS
9 | 2026-01-08 | MCS11265 | Complete servicing of aeration blowers at ETP | BRK05568 | SUSPENDED
10 | 2026-01-09 | MCS11267 | Labour and travel for maintenance of Ingersoll Rand Air Compressors in Utility | BRK05573 | REQUEST FOR OFFER
11 | 2026-01-20 | MCS11276 | Annual maintenance of boiler 1,2,3,4 & 5 | BRK05590 | PO ISSUED | PO253672 | 12460000 | MIZAMI | IN PROGRESS
12 | 2026-01-22 | MCS11277 | Disinfection of raw water and treated water tanks in Utility 1 and 2 | BRK05591 | REQUEST FOR OFFER
13 | 2026-01-22 | MCS11278 | Servicing of VAM chillers & Cooling towers 1, 2. 3, 4 | BRK05601 | REQUEST FOR OFFER
14 | 2026-01-22 | MCS11279 | Annual maintenance contract - Gas Generators in powerhouse | BRK05592 | SUSPENDED
15 | 2026-01-22 | MCS11280 | Annual maintenance contract - IR air compressors in Utility | BRK05593 | SUSPENDED
16 | 2026-01-22 | MCS11281 | Annual maintenance contract - Vam Chillers in Utility | BRK05594 | SUSPENDED
17 | 2026-01-22 | MCS11282 | Annual maintenance contract - Trane Chillers in Utility | BRK05595 | SUSPENDED
18 | 2026-01-22 | MCS11283 | Preventive maintenance of Grundfos pumps in Utility | BRK05596 | REQUEST FOR OFFER
19 | 2026-02-16 | MCS11312 | Periodic maintenance of Air - Cooled chillers and Air Dryers at Utility 1 | BRK05626/05928 | APPROVED IN BC
20 | 2026-02-16 | MCS11313 | Calibration of process instruments in Utility | BRK05627 | PO ISSUED | PO253094 | 2330600 | CALGATE | DONE | YES | YES
21 | 2026-02-16 | MCS11314 | Installation of Analyser for Nitrogen Dew Point, Moisture and Nitrogen composition | BRK05628 | PO ISSUED | PO253063 | 17969270 | NAFIX | DONE | YES | YES
22 | 2026-02-16 | MCS11310 | Cleaning of Underground Tank in Pineapple Land | BRK05624 | PO ISSUED | PO253097 | 721295 | NAFIX | DONE | YES | YES
23 | 2026-03-23 | MCS11361 | Inspection of air compressors in Utility 1 for 4 days | BRK05690 | PO ISSUED | PO253712 | 5319600 | BEAMCO | DONE | YES
24 | 2026-03-25 | PCS1100 | Installation of online pH monitoring system on raw and treated water line in Utility | FA05155 | CAPEX PO ISSUED | PO255193 | 20855000 | NAFIX | DONE | YES
25 | 2026-03-25 | MCS11373 | Maintenance of Borehole 1, 2, 4, 5, 6, and 7 Factory-wide | BRK05705 | REQUEST FOR OFFER
26 | 2026-04-02 | MCS11383 | Installation of PMS Dispenser, Calibration and Sealing | BRK05719 | PO ISSUED | PO253646 | 121475 | PUMP PLUS | DONE | YES | YES
27 | 2026-04-06 | MCS11390 | Reconditioning of 2 air compressor 113kw electric motor in Utility 1 | BRK05727 | PO ISSUED | PO255922 | 6267250 | SCHROEDER | IN PROGRESS
28 | 2026-07-24 | PCS1141 | Installation of 6m3 Softener Plant in Utility 2 | FA05166 | CAPEX PO ISSUED | PO256024 | 18300000 | CLEAKTEK | DONE | YES | YES
29 | 2026-05-21 | MCS114332 | Overhauling of pressure filter tank 1, 2, 3, 4, 5 & 6 at Utility 1 | BRK05830 | APPROVED IN BC
30 | 2026-05-29 | MCS114346 | Periodic maintenance of Air Dryers (IR & Atlas Copco) at Utility 1 | BRK05844 | PO ISSUED | PO255792 | 19964000 | DECM | IN PROGRESS
31 | 2026-06-29 | MCS114368 | Overhaul of Activated carbon filter at ETP plant | BRK05879 | PO ISSUED | PO256309 | 2500000 | NAFIX | PENDING
32 | 2026-06-29 | MCS114369 | Complete servicing of Aeration blowers at ETP | BRK05880 | PO ISSUED | PO256689 | 13032741 | WOLE OGUNS | IN PROGRESS
33 | 2026-06-29 | MCS114370 | Removal and installation of ducting system for air compressor 5 & 6 | BRK05881 | PO ISSUED | PO255926 | 5754338 | MILESTONE | DONE | YES | YES
34 | 2026-06-29 | MCS114372 | Inspection of air compressors in Utility 1 | BRK05883 | PO ISSUED | PO255920 | 1913500 | SCOA | PENDING
35 | 2026-08-03 | MCS114403 | Annual maintenance of air-cooled chillers and air dryers in Utility 1 & 2 | BRK05626/05928 | APPROVED IN BC
36 | 2026-08-03 | MCS114403 | Replacement of air filter modules on air distribution line in Utility | BRK05929 | PO ISSUED | PO256692 | 34559745 | WOERMANN | PENDING
37 | 2026-08-17 | MCS114426 | Service charges for Boiler 5 maintenance | BRK05956 | PO ISSUED | PO256680 | 752500 | MIZAMI
38 | 2026-08-17 | MCS114427 | Labour for heavy-duty preventive maintenance jobs in Utility | BRK05955
39 | 2026-08-17 | MCS114428 | Repair, verification, recalibration of Biogas flow meter | BRK05957 | PO ISSUED |  |  | NAFIX | PENDING
40 |  |  | Overhaul of Air-Cooled Chiller (CLIVET) in Utility 2 | [8 empty] | DECM, NAFIX, FADASB, MILESTONE
41 |  |  | Installation of Dampers for Boiler 5 Economizer at Utility 1 | BRK05997 | PENDING | [6 empty] | ESDDEST, FADASB, DECM, LCTL
42 |  |  | Removal, Servicing and Replacement of Borehole (Factory Wide) | BRK05998 | PENDING | [6 empty] | FADASB, TOLS ENGINEERING, DECM, MILESTONE
43
44
45
46
47
48
49
50
210719810.88

## ITEM ORDERS
S/N | DATE | MRS NUMBER | JOB DESCRIPTION | PRN NUMBER | STATUS (PENDING, PO ISSUED) | PO NUMBER | PO VALUE | VENDOR | REMARKS
1 | 2026-03-05 | ENUT006377 | 1. Cooling Tower Chemical Consumables (MAKS, VINKOCIDE, NALCO ST40) 2. UV Cleaning Chemical (Phosphric acid)
2 | 2026-03-05 | ENUT006378 | 1. TRANE Controller Upgrade (SYMBIO800)
3 | 2026-03-05 | ENUTB00662 | 1. Monoethylene glycol 2. IR Spares for Utility Air Compressors (Gearcase, Seal, etc.)
4 | 2026-03-05 | ENUT006379 | 1. TRANE Chiller Overhaul spares 2. TRANE Chiller spares for inventory (Oil, Liquid level, Transducer, EXV, High Pressure hose,etc) 3. Chiller Mechanical Tools (Manifold guage, Nitrogen guage)
4 | 2026-03-05 | ENUT006379 | 1. TRANE Chiller spares for inventory (Oil, Liquid level, Transducer, EXV, High Pressure hose,etc) 2. Chiller Mechanical Tools (Manifold guage, Nitrogen guage)
5 | 2026-03-06 | ENUT006386 | 1. Refrigerant recovery unit + empty cylinder R134A, others
6 |  |  | 1. SSR Ultracoolant oil + air filter + oil filter
7 |  |  | IR Air Compressor Spares + India
8
9
10
11
12
13
0

## Sheet1
|  | System Account ID | Email ID | CUG Line | Company Mobile Phone | System (Computer) Access | ERP Access | PTW Issuance Access | IT WIFI Access | IT Printing Access | ERP Knowledge | PTW Issuance Knowledge | Sharepoint Knowledge | HR Access Knowledge
|  | (Yes/No) | (Yes/No) | (Yes/No) | (Yes/No) | (Yes/No) | (Yes/No) | (Yes/No) | (Yes/No) | (Yes/No) | (Yes/No) | (Yes/No) | (Yes/No) | (Yes/No)
1 | Rotimi Isaac | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | Yes | Yes | Yes | Yes
2 | Adewale Sulaimon | Yes | Yes | Yes | No | Yes | Yes | Yes | No | No | Yes | Yes | No | Yes
3 | Wale Fashina | Yes | Yes | Yes | Yes | Yes | No | No | No | No | No | No | No | Yes
4 | Lekan Adedeji | Yes | Yes | No | No | Yes | Yes | Yes | No | No | Yes | Yes | No | Yes
5 | Rasheed Adeniji | No | No | No | No | No | No | No | No | No | No | No | No | Yes
6 | Chukwuma Uwabor | Yes | Yes | No | No | No | Yes | No | No | No | Yes | Yes | No | Yes
7 | Gabriel Salami | Yes | Yes | No | No | Yes | No | No | No | No | Yes | Yes | No | Yes
8 | Harrison Enabulele | Yes | Yes | Yes | Yes | Yes | No | Yes | No | No | No | No | No | Yes
9 | Tunde Mayaki | Yes | Yes | No | No | No | No | No | No | No | No | No | No | Yes
10 | Adebayo Olaniran | Yes | Yes | No | No | Yes | No | No | No | No | No | No | No | Yes
11 | Yisa Kareem | Yes | Yes | No | No | Yes | No | No | No | No | No | No | No | Yes
12 | Kunle Oyedele | Yes | Yes | Yes | Yes | Yes | No | No | No | No | Yes | Yes | No | Yes
13 | Isah Ibrahim | Yes | Yes | Yes | Yes | Yes | No | No | No | No | No | No | No | Yes